## Sheet1
Finding Theme and SRO | Recommendation |  | Action Owner | Ease of Implem-entation | Timescale | Management Response (within identified timescale) | Lead | Date due by | Status* On track Delayed Completed | Key actions and dates for delivery
Strategy | 1.1 | Ensure alignment to strategy in both business cases and communications. | Sam Proffitt | Easy | 1 - 4 Weeks | Launch refreshed business case format and guidance. | Alex Wells | 21.08.25 | On track | 30.07.25: Develop revised business case template and guidance 21.08.25: Commence re-launch of template and refreshed gudiance
SRO: Sam Proffitt | [5 empty] | Provide training and support for staff (ongoing) | Alex Wells | 21.08.25 | On track | 30.08.25: Publish template and guidance on intranet 30.08.25: Develop online video to provide overview of guidance 30.09.25: Presentation at key engagement meetings e.g. CRG
| 1.2 | Address health inequalities in future service changes, through both the strategic planning round and business cases. | Craig Harris | Moderate | 4 - 12 Weeks | Explicitly include inequalities impact assessment in commissioning intentions process and refreshed business case format | Alex Wells | 16.10.25 | On track | 16.10.25: As above and in line with revised NHSE guidance on impact assessments
Stephen Downs
Commissioning and Contracting | 2.1 | Develop a more sophisticated commissioning approach to address health inequalities, including variable payment mechanisms dependent on population need. | Craig Harris | Difficult | 12 - 26 Weeks | Review forthcoming national payment mechanism changes and consider development of aligned local approaches including integrated incentives to encourage and support neighbourhood care | Jess Williams Jane Cass Stephen Downs | 27.01.26 | On track | 23.07.25: Commissioning SLT initial discussion 15.09.25: Proposed workshop with planning, commissioning, contract management, population health and finance colleagues 30.09.25: Review of national payment mechanism changes 15.10.25: Understand the potential for VCFSE to support delivery
SRO: Craig Harris |  |  | Stephen Downs
| 2.2 | Conduct a detailed review of the capacity and capability of commissioning and finance teams to actively performance manage the LES (and other) contracts. | Sam Proffitt | Difficult | 12 - 26 Weeks | Consider capacity and capability as part of current organisational design process | Craig Harris | 27.01.26 | On track | 15.09.25: Discussions between commissioning, clinical finance and contracting teams about transitional operating arrangements to ensure integrated working 30.09.25: Agree expectations and business arrangements Sept-Oct 2025: Staff consultation is expected to begin Oct-Dec 2025: Implementation of new structures
Craig Harris
| 2.3 | Ensure joined-up commissioning between primary and secondary care with appropriate engagement for pathway redesign. | Craig Harris | Moderate | 1 - 4 Weeks | Implemented integrated contract and commissioning assurance meetings | Peter Tinson, Jayne Mellor, Fleur Carney | 21.08.25 | Completed
[6 empty] | Implemented new commissioning intentions process | Jess Williams | 21.08.25 | Completed
[6 empty] | Informed new organisational design (integrated footprint commissioning teams) | Craig Harris | 21.08.25 | Completed
| 2.4 | Consider aligning finance and contracting under a single function. | Sam Proffitt | Difficult | 12 - 26 Weeks | Consider as part of current organisational design process | Craig Harris | 27.01.26 | On track | 24.07.25: Agreed as part of overall ICB organisational design 15.09.25: Discussions between commissioning, clinical finance and contracting teams about transitional operating arrangements to ensure integrated working 30.09.25: Agree expectations and business arrangements
Industrial Action | 3.1 | Improve understanding of industrial action impacts. | Andy Knox | Moderate | 12 - 26 Weeks | Currently no industrial action underway | Wendy Lewis | 27.01.26 | Completed | 23.07.25: Ongoing. Escalation processes identified and in place, should it need to be actioned
[6 empty] | Impacts and mitigations considered as part of EPRR process | Wendy Lewis | 27.01.26 | Completed | 23.07.25: Ongoing. Escalation processes identified and in place, should it need to be actioned
SRO: Andy Knox
| 3.2 | Enhance transparency and safeguard against conflicts of interest. | Andy Knox | Moderate | 12 - 26 Weeks | Review current generic staff training and explore inclusion of specific (case study based) training for clinical and managerial commissioning staff | Claire Moore | 27.01.26 | On track | 29.07.25 and ongoing: Three training modules in place provided by NHSE. All staff mandated to complete module 1. Decision makers are mandated to complete level 2. Level 3 is for ICB chair and deputy only Transparency and safeguarding against conflicts of interest is supported through all staff providing their declaration of interests and ensuring these are managed in accordance with the policy. There is also quarterly reporting to the audit committee 30.09.25: Review compliance amongst clinical and managerial commissioning staff and report to commissioning SLT Review level 2 content and determine whether target group should be widened
| 3.3 | A clear stakeholder map needs to be developed with an agreed communications plan including key responsibilities ahead of any collaborative working or contract negotiations. | Craig Harris | Easy | 4 - 12 Weeks then on-going | Commissioning leads to review roles and responsibilities of current negotiation forums and propose any changes. | Peter Tinson Wendy Lewis Fleur Carney Jayne Mellor | 16.10.25 | On track | 30.08.25: Discuss in Commissioning SLT 30.09.25: SLT members to undertake review and report back to SLT
[6 empty] | PIDs for any significant collaborative service redesign to include stakeholder map and communications plan | Alex Wells | 16.10.25 | On track | 23.07.25: Stakeholder map and communications plan included in existing PID format 16.10.25: Engage and socialise templates with commissioning teams
Business Case Process | 4.1 | Undertake a detailed review of the new business case process and associated templates. | Stephen Downs | Easy | 1 - 4 Weeks | Launch refreshed business case format and guidance. Provide training and support for staff | Alex Wells | 21.08.25 | On track | See 1.1 above
SRO: Stephen Downs | 4.2 | Establish clear financial parameters for commissioning changes, with clarity on what requires a business case and the associated governance. | Stephen Downs | Easy | 4 - 12 Weeks | Produce a simple schematic outlining commissioning decision making arrangements and documentation required | Charmaine McElroy | 16.10.25 | On track | 30.09.25: Schematic to be developed incorporating 4.3 (governance forums for decision making), 5.2 (requirement for governance approval prior to binding communication to stakeholders) and 5.3 (limit CEO communication to final decisions, or the resolution of essential escalations)
| 4.3 | Clarify governance forums responsible for decision-making on business cases, including where Board and NED approval is required. | Stephen Downs | Easy | 4 - 12 Weeks | See 4.2 | Charmaine McElroy | 16.10.25 |  | See 4.2
| 4.4 | Ensure all financial numbers are validated and properly included in the business case for decision making. | Stephen Downs | Easy | 1 - 4 Weeks | Refreshed business case format and guidance to reinforce requirement for finance engagement and sign off | Alex Wells | 21.08.25 | Completed | 23.07.25: Gateway stages for finance engagement and sign off included within business case format and guidance
Leadership | 5.1 | Define the responsible Executive from the outset. | Craig Harris | Easy | 1 - 4 Weeks | Commissioning executive responsible for all commissioning proposals | Craig Harris | 21.08.25 | Completed
SRO: Sam Profitt |  |  | Sam Proffitt
| 5.2 | Avoid binding correspondence with stakeholders before governance approval. | Craig Harris | Moderate | 1 - 4 Weeks | See 4.2 | Charmaine McElroy | 21.08.25 |  | See 4.2
| 5.3 | Limit CEO communication to final decisions, or the resolution of essential escalations. | Craig Harris | Easy | 1 - 4 Weeks | See 4.2 | Charmaine McElroy | 21.08.25 |  | See 4.2
Communication and Stakeholder Management | 6.1 | Improve formal and informal communication to facilitate negotiation, see recommendation 3.3. | Craig Harris | Difficult | 12 - 26 Weeks | See 3.3. In response to new organisational design review informal and formal communication touch points | Peter Tinson Wendy Lewis Fleur Carney Jayne Mellor | 27.01.26 | On track | See 3.3 Subject to agreement of organisational design
SRO: Craig Harris | 6.2 | Balance collaborative approaches with effective negotiation. | Craig Harris | Difficult | 12 - 26 Weeks | See 3.3 | Peter Tinson Wendy Lewis Fleur Carney Jayne Mellor | 27.01.26 | On track | See 3.3