## Slide 1: The Mental Health, Learning Disability and Autism Inpatient Quality Transformation Programme Plan for Lancashire and South Cumbria 2025-2027

## Slide 2: Lancashire and South Cumbria MHLDA Inpatient Quality Transformation Programme Aim
Lancashire and South Cumbria are committed to the NHSE National programme deliverables of improving the quality and safety of care people experience in mental health, learning disability and autism inpatient settings by introducing a new bold, radical and re-imagined model of care for the future.
Dedicated efforts continue across the Lancashire and South Cumbria system to:
localise and realign MHLDA inpatient care,
improve the quality oversight and support offer for inpatient services facing challenges,
build upon the work that has been done to improve the culture of care by making services more culturally appropriate, trauma-informed and autism informed
reduce restrictive practice within MHLDA inpatient settings
By April 2027, Lancashire and South Cumbria will deliver a high quality, equitable and least restrictive MHLDA inpatient system by:
Eliminating inappropriate out of area placements,
Reducing inpatient length of stay across adult acute, rehabilitation and LD/A pathways
Reducing the number of people in inpatient care year on year
Strengthening community alternatives and flow, so that people are admitted only where care can only be delivered in an inpatient setting and are supported to leave hospital as soon as they are clinically ready, with progress measured through agreed trajectories for bed use, length of stay, CRFD, out of area placements, patient experience and quality outcomes

## Slide 3: Introduction
The Mental Health, learning Disability and Autism Inpatient Quality Transformation Programme (MHLDA QTP) was launched in April 2024 to improve the quality and safety of mental health, learning disability and autism inpatient services, including ensuring that all people can access care for their needs, locally, quickly and wherever possible in the community.
Lancashire and South Cumbria Integrated Care Board have worked collaboratively with Lancashire and South Cumbria NHS Foundation Trust, Local Authorities and system partners to review the significant work that has already been undertaken to achieve the aspirations of the MHLDA QTP and agree the priorities for redesigning and re-commissioning mental health, learning disability services by April 2027.
The scope of this work aligns to the NHS England » Commissioning framework for mental health inpatient services
The following plan will set out the aspirations, key achievements to date and actions required over the next two years to re-design adult mental health inpatient services, adult mental health rehabilitation services and acute inpatient mental health services for people with a learning disability and autistic adults in Lancashire and South Cumbria.
This plan focusses on the following 3 areas of work:
Areas of Focus | Quality Inpatient Offer | Flow Through Inpatient Services | Community Alternatives
Aim | Ensuring access to good quality, evidence-based care and intervention from a diverse multi-disciplinary and multi-agency offer in the inpatient setting | Ensuring people are in an inpatient setting for as short a time as possible and then supported in the community as soon as they are ready. This will free up local bed capacity for people that require it, reducing unintentional harms of people waiting, staying longer than is needed or going out of area. | Providing a good quality, multi-agency community offer that works together to wrap around the person and their loved ones, providing early and preventative intervention and promoting citizenship and a sense of belonging. This offer is essential in ensuring people can also leave hospital when they are clinically ready.

## Slide 4
Vision | We will localise and realign inpatient services, harnessing the potential of people and communities. This will include only commissioning mental health inpatient care that is inclusive of services for learning disabilities and autistic people, that is in line with the commissioning framework and where there is an evidence base and quality can be assured. We will ensure admissions to a mental health hospital are for assessment and treatment that can only be delivered in an inpatient setting. |  | 
Strategy | Service Redesign of inpatient provision | Re-Commissioning of inpatient provision | Strengthening of the community assets, services and system working to reduce the reliance of inpatient care
Areas of Focus | Quality Inpatient Offer | Flow Through Inpatient Services | Community Alternatives
QTP Principles | Valuing | Accessible | Humane | Equitable | Therapeutic | Lived Experience Engagement | Collaborative | Citizenship
QTP Enablers | Data and Intelligence |  | Workforce |  | Improved Collaboration, Leadership & Governance |  |  | 
LSC Design Plan (Adult MH, Rehabilitation, Learning Disabilities and Autism)
QTP Phases | Year Two (25/26) |  |  |  | Year Three (26/27) |  | 
 | Establish | Review | Redesign | Implement | Evaluate | Refine | Sustain
Pledge | We will ensure that the design, development and delivery of this plan will be co-produced with people with lived and living experience of receiving care, and of those people working within services. There will also be a specific focus on meeting local population health needs and addressing inequalities. |  |  |  |  |  | 

## Slide 5
Adult Mental Health inpatient services (adult/older adult acute & PICU) | Mental Health inpatient Rehabilitation | Acute Mental Health inpatient services for adults with a learning disability and autistic adults | Consideration for autistic adults
Significant reduction in inappropriate out-of-area placements, supporting care closer to home. Acute bed remodelling completed, with current bed usage consistently below projected targets. Embedding of the Culture of Care programme across five wards in LSCFT, leading to improved patient experience and a reduction in restrictive practices. LSCFT Ward accreditation framework developed and embedded, ensuring consistent quality standards. Ongoing improvement work on care planning in LSCFT, including the implementation of DIALOG+ to support shared decision-making. Launch of the Patient First Programme and establishment of the Inpatient Improvement Forum to drive continuous improvement. Development of a patient engagement portal, promoting transparency and co-production. Use of SafeCare on LSCFT wards, supporting safer staffing and real-time decision-making. Implementation of 10 High Impact Initiatives, including weekly MADE to improve patient flow. | LSCFT Community rehabilitation clinical model developed and approved, supporting a shift to more localised, person-centred care. Business case submitted for the creation of four locality-based community rehabilitation teams. Spot-purchased rehabilitation placements reviewed and reduced, supporting more consistent and sustainable provision. Weekly oversight meetings established to monitor rehabilitation flow and discharge planning. Rehabilitation dashboard developed, enabling tracking of length of stay and Community Ready for Discharge (CRFD) status. Review of individuals with inpatient stays over 365 days underway, with a focus on reducing length of stay and improving outcomes. Engagement with independent sector providers to ensure alignment with national rehabilitation guidance. Collaborative planning with supported accommodation, Local Authorities, and community rehabilitation teams to improve flow into supported living. Close working with ICB colleagues to increase the frequency and effectiveness of rehabilitation MADE meetings. Rehabilitation tracker implemented, capturing data on patient pathways and supporting clarity of admission purpose. | Inpatient numbers reduced, with trajectory targets successfully met. Improved position against the national inpatient target. Extensive demand, capacity, and workforce modelling completed to support the development of Water Meadow View, a new 14-bed inpatient unit scheduled to open in LSCFT in November 2025. Community infrastructure enhanced, including Intensive Support Teams (IST) and discharge coordination functions. Model of care developed for community services, supporting consistency and improved outcomes. Addressing unwarranted variation in community service delivery and investment to ensure equity and effectiveness. Strategic housing planning underway, supporting sustainable discharge and recovery pathways. Established links with HOPES, promoting least restrictive care and improved flow. Enhanced commissioning for advocacy, ensuring patient voice and rights are embedded in care planning. | Increasing recognition of autistic individuals within inpatient care across LSCFT, with a focus on tailored, person-centred approaches. Rapid learning reviews initiated for all readmissions, supporting continuous learning and service improvement. Specialist autism team in LSCFT actively engaged in the development of a business case to enhance support and provision. Autism-informed care training programme in development, aimed at upskilling staff across inpatient services. Community support gaps identified and acknowledged, informing future planning and commissioning. Dedicated LD/A matron embedded within mental health inpatient services, providing leadership and advocacy. Specialist autism team in-reaches into inpatient services, offering advice, consultation, and recovery-focused support. Green Light Toolkit implemented and audited across all mental health inpatient wards, ensuring services are accessible and responsive to autistic individuals.
LSCFT five-point plan implemented that addresses the MHLDA QTP deliverables, including development of Patient Pathways, Strengthening Community-Based Mental Health Services, Trusted Assessment and Community Capacity, Reshaping the LSCFT Bed Model and Reducing Housing and CRFD delays. In addition, a new Section 117 policy is being co-developed by four Local Authorities in partnership with the ICB and LSCFT, ensuring a consistent and person-centred approach to aftercare. |  |  | 
LSC Year One (2024/25) Progress (Adult MH, MH Rehabilitation, Learning Disabilities & Autism)

## Slide 6
Service Development Funding in 2024/25 was prioritised to strengthen and transform the adult mental health rehabilitation pathway across Lancashire and South Cumbria. This investment supports delivery of key Quality Transformation Programme (QTP) objectives focused on improving inpatient flow, enhancing community alternatives, and ensuring more timely, person-centred discharge planning. This includes:
  Rehab Core Team – providing centralised oversight and coordination of the rehab pathway, supporting consistent case tracking, barrier resolution, and strategic leadership across localities.
  Wesham Level 2 Rehab – delivering a targeted inpatient rehabilitation offer for individuals with complex needs, supporting recovery-focused care, clear discharge pathways, and reduced length of stay for those previously placed out of area.
  Community Rehab Support – strengthening step-down provision and community-based rehab capacity, including enhanced multi-agency discharge planning and wraparound support to enable sustained recovery outside hospital.
These initiatives are designed to be scalable and sustainable, with alignment to national rehab guidance, local demand and capacity modelling, and ongoing work to reduce out-of-area placements and improve outcomes for people with long-term rehabilitation needs.
As we continue to collaborate across the North West through a single programme approach, there is a valuable opportunity to share learning, strengthen alignment, and drive meaningful outcomes at scale.
Year one QTP funding spend

## Slide 7: A governance structure was developed to support the 3 systems in the North West with the MHLDA QTP and LSC system has been fully engaged in these forums

## Slide 8: LSC MHLDA inpatient position September 2025
Metrics | Adult Mental Health (inclusive of older adult and PICU beds) | MH Rehabilitation | Acute Mental Health inpatient services for adults with a learning disability and autistic adults | Autistic people within MH inpatient services | Autistic people within MH inpatient services
Progress to date | Out of area bed use (spot): Contracted bed use in IS: 109 reduced to 71 (30/09/2025) | Out of area bed use (spot): data quality and oversight improved Contracted bed use in IS: 94 reduced to 77 | Total beds 92 reduced to 54 Autistic people inpatient reduced from 39 to 30 People with a LD and Learning disability and autism in inpatient care has reduced from 41 to 24 |  | 
Current bed base | Out of area bed use (spot): zero Contracted bed use in IS: 71 LSCFT acute beds: 468 Total: 539 | Out of area bed use: 31 Contracted bed use in IS: 77 LSCFT beds: 24 Total: 132 | Total: 24 | Total: 30 | 
National deliverables | Eliminate inappropriate out of area placements Reduce Length of stay in inpatient care | Submit a trajectory for ceasing the commissioning of ‘locked rehabilitation’, inpatient care that is outside of the commissioner guidance and is not part of a local pathway of care by December 2025 | Reduce inpatient admissions/ stays by 10% year on year (current target for LSC is 40 based on 30 people inpatient per million population) |  | 
Next steps in setting trajectories | Build on demand and capacity modelling to determine the number, type and location of MHLDA beds needed to meet population health needs and address health inequalities Focus on improving flow across inpatient provision, agreeing on trajectories related to reducing Length of Stay, Clinically Ready for Discharge and waits for inpatient care Identify areas for development and improvement to support providing more care and support in the community to reduce reliance on inpatient care |  |  |  | 
There continues to be significant efforts across the system to ensure that:
People can access earlier intervention and preventative support in the community reducing reliance on MHLDA inpatient care
People are only in a MHLDA hospital for a need that can only be addressed within an inpatient setting
People can get timely access to a local MHLDA inpatient service when they need it
People receive good quality inpatient care that optimises their recovery and reduces the time they spend in hospital
People can leave hospital when they are clinically ready
Best use is made of available resource
Targets and trajectories will be developed to track these deliverables (including patient reported outcome and experience measures) over the next 6 months:

## Slide 9: LSC plan for delivering the MHLDA Inpatient Quality Transformation Programme
The ICB has carefully considered the Inpatient Quality Transformation Programme and have identified the following commissioning intentions that will support achievement of the 3 year plan:
Develop neurodevelopmental pathway (adult autism/ADHD) and business case for services, including a needs-led support offer, transition and triage.
Development and delivery of a three-year transformation plan to substantially improve outcomes for people with mental ill health through the delivery of support for:
  Those people experiencing a Mental Health Crisis – through delivery of the Urgent and Emergency Care Implementation Programme
  People in need of an acute and/or intensive assessment, treatment and rehabilitation service by ensuring that this is offered as close to, or at, home reducing the requirement for people to go outside of LSC to access inpatient services –improving the basic care offer, clinically evidence pathways through Patient First work, Home Based Treatment Team improvement work and embedding lessons learned through the Culture of Care work
  Continued growth and development of the Community Mental Health Transformation Programme – developing the community rehabilitation offer, ensuring easy access to services for our most vulnerable and unwell residents, ensuring we have an effective and assertive support response for people who are most at risk

## Slide 10: LSCFT’s Five-Point Plan to drive delivery of the Inpatient Quality Transformation
Five-point plan | Objective | Key actions
1. Patient pathways programme to improve care and reduce Length of stay (LOS) and bed occupancy. | To deliver Best Possible Care: Clinically led Patient First group focused on implementing evidence-based standards of treatment across our inpatient wards. Focus on Emotionally Unstable Personality Disorder (EUPD) and psychosis pathway with clinical pathway redesign | Productivity and improving ward processes – Worden ward -Initial focus on the Psychosis pathway, covering Schizophrenia, Bipolar, and Depression in the first year due to frequent admissions and extended stays Stranded & super stranded IMG- Extended to April 25-March 26. The IMG is in the process of finalising the metrics/reduction targets and areas of focus for 25-26
2. Strengthen community-based MH services to tackle avoidable admissions and support earlier discharge. | Improving Home Based Treatment Team (HBTT) offer – treating people at home, avoiding an admission, facilitating early discharge. Developing Community Rehabilitation capacity as an alternative to longer-stay wards and enhancing CMHT productivity and effectiveness to help prevent deterioration to the point where admission is required. | Undertaking HBTT capacity and demand mapping HBTT Caseload - Networks cleanse of HBTT caseloads Access Criteria review of community services to understand in-network and across network variation. Implementing Trusted Assessment - Work required being scoped Community Rehabilitation Teams - Implement Community Rehabilitation Teams as an alternative to longer-stay wards Voluntary, Charity, Faith and Social Enterprise (VCFSE) & Mental Health Additional Role Reimbursement Scheme (ARRS) capacity - Improve effectiveness of additional VCFSE & ARRS community capacity and ensure each locality is aware and utilizing the VCFSE offer Ongoing challenges with current ARRS contracts to be monitored via LSCFT and ICB ARRS working group. Updates are fed into the CMHT workforce group and transformation board
3. Reshape LSCFT Bed Model | The Trust is currently reviewing the population’s rehabilitation needs, Older Adult demand and PICU demand to support a reshaping of the inpatient bed base. The Trust has invited the national GIRFT team to support this review and to provide external and independent assurance. | Adult & Older Adult NHS benchmarking analysis - a review of the bed stock / revised bed model CYP benchmarking Review bed stock with recommendations to clinical standards Rehab contractual position and ICB: ICB Rehab Lead involved in LSCFT bed modelling work and Getting It right First Time (GIRFT) discussions, to incorporate independent sector capacity and pathway management into overall rehab pathway management.
4. Develop innovative solutions to housing needs of patients on discharge. | In partnership with the ICB and local authority colleagues develop solutions as the impact on mental health of poor-quality housing or complicated living arrangements is well evidenced as a significant issue. Gaining tenancies can be a challenge for patients with forensic histories, particularly where substance use or arson are a factor. A Joint Housing Strategy, signed up to by all partners, including the ICB, District Councils/ Unitary Authorities and the NHS and a collaborative approach to address some of the housing issues as a system. This has been raised with ICS and ICB colleagues for consideration. | Housing work / paper - Overview of all the workstreams currently underway to support with identifying and assisting any housing needs for patients as early as possible and ensuring reliable connections and resources are in place for patients to access on discharge. Step Down Beds - stepdown provisions paper was recently approved at an executive team meeting which will look at stepdown facilities being co funded by the districts and local authority, we are currently awaiting further financial details.
5. Work with ICB and Local Authorities to reduce CRFDs by 50% | CRFD numbers increased from a range of 70-90 in 2023 to 100-120 in 2024. With increased senior focus, there is a target to reduce CRFD by 50%. | Multi Agency Discharge Events (MADEs) - A terms of reference has been developed and weekly MADEs are now established with tier 1 and tier 2 alternating on a bi-weekly basis. Development of Joint Discharge support post Commencement of Discharge Rapid Improvement events – internal / external events and learning to be shared

## Slide 11
Areas of Focus | Quality Inpatient Offer |  | 
Aim | Ensuring access to good quality, evidence-based care and intervention from a diverse multi-disciplinary and multi-agency offer in the inpatient setting |  | 
Inpatient area | Adult Mental Health inpatient services (including adult/older adult acute & PICU) | Mental Health inpatient Rehabilitation | Acute Mental Health inpatient services for adults with a learning disability and autistic adults
Objectives & Outcomes | Implementation of QTP National mental health acute care guidance Address workforce gaps and support therapeutic interventions. Develop pathways of care for CEN and substance misuse needs Focussed work to support reviews of people stranded and super-stranded in inpatient care. Royal College of Psychiatrists ward accreditation. | Complete baselining of the number of beds commissioned by LSC for rehabilitation , including activity, financial envelope and individual need Identify gaps in current commissioned provision and use demand and capacity modelling, available data and clinical expertise to inform a trajectory and plan for a new pathway of care (ceasing the commissioning of locked rehabilitation, outdated models of care, and inpatient care that is outside of a locally commissioned pathway). Implementation of QTP National mental health inpatient rehabilitation commissioner guidance across commissioned inpatient provision Develop shared specifications and processes to reduce variation across LSC Strengthen co-production and lived experience involvement. | Implementation of QTP National guidance for Acute Mental Health inpatient services for adults with a learning disability and autistic adults Work across NW footprint to define and develop a baseline for LD rehabilitation and consider how the needs of this group could be better met when they are in acute services to minimise additional transitions/ time away from home. Work across NW footprint to develop consistent inpatient processes/practice Ongoing evaluation of workforce skills/ competencies and opportunities for developing the therapeutic offer when Water Meadow View Unit opens to admissions.
Considerations for autistic people | Implementation of relevant sections within inpatient guidance, eg reasonable adjustments and Green Light Toolkit Identify gaps in workforce competency and training needs and expand autism-informed training across inpatient teams. Map out current specialist autism support/consultation for general mental health provision Ensure inpatient environments are therapeutic and support a person's recovery Develop reporting structures to improve data and oversight |  | 
Quality Enablers | Continue embedding Culture of Care standards across all inpatient wards. Implementation of ‘I and We statements’ within commissioned services to inform improvements Embed Early Warning Signs reporting structures and Home and Placing Commissioner Guidance Implementation of Ward accreditation in LSCFT |  | 
LSC Plan- Key actions to improve the quality of the MHLDA inpatient offer

## Slide 12
Areas of Focus | Flow through inpatient services |  | 
Aim | Ensuring people are in an inpatient setting for as short a time as possible and then supported in the community as soon as they are ready. This will free up local bed capacity for people that require it, reducing unintentional harms of people waiting, staying longer than is needed or going out of area. |  | 
Inpatient area | Adult Mental Health inpatient services (including adult/older adult acute & PICU) | Mental Health inpatient Rehabilitation | Acute Mental Health inpatient services for adults with a learning disability and autistic adults
Objectives & Outcomes | Implementation of the 10 high impact initiatives Improve data integration and flow tracking (e.g. length of stay, discharge readiness). Strengthen links between inpatient and community services to improve flow. Involvement in NW mental health Leaning and Improvement Network (LIN) to reduce long LOS. Lester tool roll out across all inpatient wards. Working towards same day admissions, improved clinical outcomes and reduced LoS to 40 days in Adult, 90 days in Older Adult and 37 days in PICU Inpatient wards by June 2028 Use MADE and Super MADE to escalate delays to discharge and overcome barriers as a system | Implementation of the 10 high impact initiatives, including focussed work to improve Purpose of admission, expected date of discharge and CRFD reporting Inclusion of rehabilitation cases (in and out of area) in system MADE’s Improved data from all commissioned inpatient rehabilitation services via NW dashboard and local data developments Ensuring there isn’t unwarranted variation in outcomes for different groups of individuals and any health inequalities are addressed | Finalise transition plans for Water Meadow View admissions. Continue reducing long-stay inpatient population. Use 12 point discharge plan Utilise C(E)TR processes to support discharge planning Utilise CRFD reporting and MADE meetings to support system escalation Embed Section 117 policy and discharge pathways.
Considerations for autistic people | Address identified gaps from Green Light Tool Kit inpatient audits Utilise C(E)TR processes to identify and address barriers to discharge Strengthen VCFSE and community support to reduce length of stay |  | 
Quality Enablers | Tracking of inpatient metrics, including planning metrics to understand flow and any unwarranted variation Identification of any inequalities in inpatient metrics for different groups, eg via Patient and Carer Race Equality Framework Staff surveys, workforce data and other quality metrics that may impact on flow |  | 
LSC Plan- Key actions to improve flow through inpatient services

## Slide 13
Areas of Focus | Community Alternatives |  | 
Aim | Providing a good quality, multi-agency community offer that works together to wrap around the person and their loved ones, providing early and preventative intervention and promoting citizenship and a sense of belonging. This offer is essential in ensuring people can also leave hospital when they are clinically ready. |  | 
Inpatient area | Adult Mental Health inpatient services (including adult/older adult acute & PICU) | Mental Health inpatient Rehabilitation | Acute Mental Health inpatient services for adults with a learning disability and autistic adults
Objectives & Outcomes | Strengthen links between inpatient and community services including better working across teams and collaborative working with VCFSE, Housing and Local Authorities LIN improvement project to test improved housing/LA working to facilitate timely discharge Develop a strategic housing plan to support the delivery of care in the community Ensure work is aligned to LSC UEC plan and supports the development of home based treatment teams to offer responsive and preventative intervention, achieving core fidelity of the national model Ongoing improvement work to strengthen the purpose of admission into adult mental health inpatient care, ensuring a ‘community first’ approach is embedded consistently across LSC | Benchmark community rehabilitation services against national guidance and develop trajectories for commissioning a local pathway of care that addresses a person’s rehabilitation needs in the community. Secure approval and funding for community rehabilitation business case and expand the offer to cover all localities (e.g. Blackburn and Darwen) and increase the caseload by 1/3 by March 2027 Implementation of QTP National mental health community rehabilitation commissioner guidance Refine process for 72hr follow up in line with 10 High Impact Initiatives to ensure after care arrangements are appropriate to meet the person’s needs and minimise risks of relapse/ readmission. Strengthen relationships with VCFSE and Housing providers to provide early intervention and preventative support, to reduce inpatient admissions and longer lengths of stay in hospital. Improve step-up/step-down pathways and community alternatives. | Improve early intervention and community wrap-around support. Improve community alternatives and crisis response. Strengthen joint commissioning with local authorities. Identify opportunities for greater multi-agency service delivery with VCFSE partners Develop a strategic housing plan to support the delivery of care in the community Ensure developments are aligned to the national plan to develop the Intensive Support Function (ISF) To continue to utilise the Dynamic Support Register to identify opportunities for increased community support to prevent unnecessary admission to hospital
Considerations for autistic people | Expand autism-informed training across community team and improve early intervention and community wrap-around support. Develop crisis response pathways tailored to autistic individuals. Strengthen integration between mental health and autism services. Ensure appropriate placement availability and support for discharge planning. |  | 
Quality Enablers | Increased access to a range of therapeutic assessments and interventions at a level of intensity that will meet the individual need eg, via Intensive Assertive Treatment 24/7 Hubs, implementation of the Personalised Framework Increased collaboration across services and appropriate leadership, governance and oversight |  | 
LSC Plan- Key actions to develop community alternatives to inpatient care

## Slide 14: LSCFT: Continuing to improve the culture of care across inpatient services
Programme Involvement:
LSCFT is involved in 5 of the 6 national strands of the Culture of Care programme.
Five wards are actively participating in the ward-level Quality Improvement (QI) strand, the largest cohort nationally.
Two ward managers have completed the Ward Manager Development Programme; three more are starting in September.
Lived Experience and Co-production:
Four lived experience leads are aligned to the five wards.
Service user councils and feedback forms are embedded in ward routines.
Co-produced standards and the “Culture of Care House” model are being used across wards.
Quality Improvement Initiatives:
Over 40 change ideas have been tested across five wards.
Examples include scheduled Multi-disciplinary Team slots for patients, autism-friendly recipe cards, sensory gardens, and seclusion resource boxes.
Staff and patients have co-designed improvements to ward environments and ward processes.
Training and Development:
Staff have received training in trauma-informed, autism-informed, anti-racism, and cultural competence approaches.
A dedicated practice educator supports implementation across wards.
Peer support workers and volunteers are being integrated into ward teams.
Data and Outcomes:
Positive trends in patient experience and reduced restrictive practices (e.g. restraint, seclusion).
Mini burnout surveys show high job satisfaction despite stress.
Accreditation visits aligned with Culture of Care standards are underway across all 47 inpatient wards.
Progress to Date:
Expand the Culture of Care programme beyond the initial five wards.
Embed the “I & We” statements across all inpatient services.
Strengthen the role of lived experience in governance and service design.
Continue to track and evaluate impact using national dashboards and local metrics.
Secure ongoing funding and support for key roles.
Align with national and regional developments, including the Royal College of Psychiatrists’ frameworks.
Priorities for Year 2:

## Slide 15
Sept 2025
Jan 2026
April 2026
Q4
Q3
Q1
Application of Demand and Capacity Models
Embedding of QTP Principles
e.g. via “I”& “We” Statements and Culture of Care
ICB Commissioner and Contract Leads Identified
Plan for MH Act Reform
Map out and plan for QTP Interdependencies ABI, Secure, CERN, CYP, VCSFE
Agree ICB reporting and escalation processes for System Oversight (inc. Early Warning Signs)
Plans for Culture of Care Sustainability
Define All Elements to be Included in Specifications
Inpatient access processes
Development of models of care
Definition of KPIs and reporting mechanisms to be incorporated
Plan for implementation and decommissioning
Regular reporting until March 2027
Implementation of guidance (inc. QTP Principles)
Implementation of model of care
System Oversight (inc. EWS) Implementation Plan
Established Programme Governance and Delivery Groups
With defined aims, action plans and roles and responsibilities
Established Baselines and Setting Trajectories
Completed Assessment against QTP Guidance and Requirements
Understanding of system gaps, best practice, ensure alignment
Define Lived Experience Involvement and Plans for Coproduction
Determine existing channels and processes to support effective System Oversight
Consolidate Culture of Care Activity
Identifying progress, lessons learned and future opportunities for sustainability
Quality Transformation Programme (QTP) – Key Milestones

## Slide 16
Sept 2026
Jan 2027
April 2027
July 2026
Local Pathway of Care Commissioned in line with the Commissioning Framework:
Adult Mental Health (inclusive of older adult and PICU)
Acute Mental Health inpatient services for adults with a learning disability and autistic adults
Inpatient Mental Health Rehabilitation- Level 1 & 2, (inclusive of inpatient rehabilitation for people with learning disabilities and autistic people)
Contracts in Place, Specifications Developed (autism-informed), Agreed KPIs and Reporting Mechanisms, QTP Principles Embedded, Plan for Service Sustainability, Plan for Service Evaluation
Robust Community Services
Q4
Q3
Q2
Implementation of Redesigned Pathways
Contract and Specifications Finalised
Autism-informed, trauma informed and aligned to QTP objectives and principles (inc. “I” and “We” Statements)
KPIs/ Reporting Agreed
Alignment to Commissioning Intentions
Draft Specifications Agreed and Signed Off
Taken through appropriate governance channels
Identification of Bed Capacity to Inform Contracts
Understanding of Workforce Requirements
Agree VCSFE Interface
Clear Processes for System Oversight and Governance
Culture of Care Principles Embedded
End of Programme
Quality Transformation Programme (QTP) – Key Milestones

## Slide 17
This plan has been approved by: | Date | Signed | Name/role
Lancashire and South Cumbria ICB via ICB Board | 23/01/2026 | Kate OSullivan | Head of Recovery and Transformation – Mental Health
Lancashire and South Cumbria NHS Foundation Trust | 30/01/2026 | Oliver Soriano | Chief Nursing Officer
The Senior Responsible Officer for the MHLDA Inpatient Quality Transformation Programme in Lancashire and South Cumbria is Kate O’ Sullivan, Head of Recovery and Transformation, NHS Lancashire and South Cumbria Integrated Care Board.
Dedicated support to meet the deliverables of the Inpatient Quality Transformation Programme is provided from Clair Haydon, Clinical Director for Mental Health Complex Care for Northwest England and Fiona Jones and Rosie Lawson, Inpatient Quality Transformation Project Managers.
The Programme of work will report into the Lancashire and South Cumbria Mental Health Transformation Board.
Approvals and Governance