## Slide 1: Lancashire and South Cumbria Children and Young People’s Neurodevelopmental Pathway Transformation Update
January 2026

## Slide 2: Lancashire & South Cumbria position for autism and ADHD pathways for children and young people
Increased referrals
Long waiting times for assessment
Gaps in compliance with national guidance
Inconsistent support for families
Fragmented pathways, silo working and lack of funding
Increased use of private assessments with no oversight of quality
High number not receiving a diagnosis at end of the pathway

## Slide 3: What have we been doing?
Ran a Stakeholder Expert Group in 2024 to lead developments
System wide workshop listening​ events
Commissioning framework agreed​
New minimum diagnostic standards have been agreed
ND Programme Board in place to give system ownership
Additional resource agreed across ICB

## Slide 4: ND Service Transformation – what do we want the service to offer:
Single front door
Fully digitalised
No service handoffs / parallel waiting lists
Consistent approach to diagnosis
Pathway Navigators embedded
ND profile / plan bespoke to each child at earliest opportunity
Connected to local support offers
Skilled workforce across health, social care and education – Shared language and understanding

## Slide 5
Needs led support hub
SEND Local offer
Websites, apps, leaflets, resources
Universal support/services e.g. welfare, benefits, employment, health professionals, nurseries, school, social care, CYPS
Self-help and peer support groups
Carers centres
ASD/ADHD training offer
Resource materials
Pre-diagnosis early years help, Triple P, Stepping Stones
Multi-disciplinary team meetings
Digital Profiling tool completed by relevant professional
Phase 2: Screening and Pathway Navigator allocation
Phase 3: Single hub team triage
Phase 3: Local MDT Model for Complex Referrals
Onward to alternative
service e.g. CYP MHS, Community Paediatrics
Phase 4: Specialist assessment:
ASD
ADHD
FASD
Phase 5: Conclusion of assessment pathway
Ongoing intervention and support plan updated
Diagnosis
Lead professional informs child/young person, family and referrer
Intervention, review and transitions
Phase 1: Concerns identified or support required
Speech & Language Therapy
Sensory Support
This model has 4 main components:
Open access resources to better help people determine where best to seek support and understand their own needs (all age).
Single point of access to an MDT, who will determine whether to accept the person, and if so whether to use a profiling tool to screen for diagnosis, and / or signpost, or refer, to a range a graded supports. The team will join up any supports.
Access to a ‘bubble’ of community based supports, public sector and VCFSE, supports, tailored according to need (all age, specific offers for adults)
For those that require it, access to NICE compliant diagnoses for the principal ND conditions.
Development of individual support plan
CYP ND Diagnostic
Hub

## Slide 6
Needs Identified
Signposting to local hubs for support offers
Support put in place
Profiling Tool
Digital tool completed by family & professionals
Interventions put in place
Referral
Digital referral completed by professional once support offers accessed
Screening & Triage
Pre-assessment
Assessment
Ongoing Care
Assessment of suitability by MDT
Further information requested from education (where possible) & parents
Signposting to local support services
Waiting list
Pathway navigator support
Diagnostic assessment by relevant team(s) according to agreed minimum standards
Individual support plan updated
Medication for ADHD
Signposting to support
Individual support plan created
Pathway navigator assigned?
Allocation to waiting list where appropriate
Referral back to support hubs or to ongoing care
Shared care/monitoring arrangements
Local Support Hubs
Enablers: Service specification, reporting, digital solution

## Slide 7
LSC Children's Commissioning Network
Digital Stakeholder Group
Needs led support offer (including sensory)
Transformation of delivery model & WLI
Upskilling, training and education
Communication and engagement
4x SEND Partnership Boards
1x SEND Improvement Board
ND Programme Board (Bi-Monthly)
Stakeholder Expert Group, Parent carer meetings, LSC Community Neurodisability Network, Community Paediatrics T&F Group
Complex Case Pathway
Sensory offer
Profiling Tool

## Slide 8: Workstream Updates
Transformation | Needs Led Support​ | Training and Education | Comms & Engagement​ | Digital​
Diagnostic & Assessment Standards agreed across system​ Initial Service Spec - review and development​ Engagement sessions ongoing with MH, LD&A and Community Paediatricians​ Proposal to move to single Diagnostic Hub model for whole system –​ Multi-disciplinary service ​ Fully digitalised​ Robust focus on high quality triage ​ Built on strong offer of support services​ Covers ASD, ADHD and FASD ​ Ongoing discussion around LD diagnosis | Funding for additional support secured and providers identified through collaboration with Spring North Match funding application underway with National Lottery.​ Use of Lot A/Lot B services – Consideration of how Lot A services can integrate into existing services.​ Tiers of support / continuum of access and Support Charter under development.​ New Sensory support offer under development.​ Scoping exercise & digital catalogue of all support services underway by each LA - heat map of service offer and gaps.​ | Agreement of training principles across system.​ Mapping exercise underway to understand different offers and training gaps.​ Development of training models and minimum requirements at universal, targeted and specialist levels.​ Multi-agency training strategy to be developed.​ System-wide commissioning of clinical training to improve clinical knowledge and consistency e.g. ADOS.​ | Co-produced Communication Strategy under development. ​ Multi-stakeholder session occurred on 7th August.​ Aligns to wider SEND comms strategies.​ ND section operational on ICB website and links to Local Offers.​ Survey undertaken to map communication groups to streamline comms.​ Public facing ‘ND update’ statement in development. ​ | Development of a Digital Referral Form (building on work already undertaken)​ App development underway for referral and management of pathway​ Pilot to be undertaken in BTH of digital solution​ Digitalisation of profiling and screening tool​ Work underway to connect support services into a digital catalogue to make support services bespoke based on ND profile and wider demographics​ Three key delivery groups agreed:​ Compliance (IG)​ Clinical (triage development and Digital Referral form)​ Delivery (pilot)​

## Slide 9: Transformation Workstream
Service Specification based on the new model has been reviewed collectively by range of clinical and non-clinical leads.
Final points of clarity being explored.
KPIs supported and reporting arrangements being finalised.
Pathway Navigator function incorporated in to new service offer, details of role and function to be agreed.

## Slide 10: Digital pilot
A 6-month pilot due to commence 2nd March 2026 in Blackpool.
The system will streamline early pathway stages, enhance school involvement, improve triage quality and standardisation, reduce clinical admin burden, and improve experience for families, clinicians, and educators. The scope includes the following applications:
    Referral (Single Point of Access/Digital Front Door)
    ND Strengths & Needs Assessment (profiling)
    Triage
It is hoped that the pilot will prove that the digital platform provides a better system in terms of:
    Costs reduction - A reduction in CYP coming through to the diagnostics stage due to measures being put into place for earlier support (reasonable adjustments which are automatically generated from the profiling tool)
    Utilisation – Less burdensome on admin time at BTH (work has previously been undertaken to cost out the entire journey, it is anticipated that digitalisation will reduce this

## Slide 11: Right to Choose
Growth in use of RTC.
Lancashire and South Cumbria position statement to be finalised to support clear messaging for families, GPs, schools, health providers.
Accreditation process to be implemented by the ICB to enable quality assurance of RTC providers against local requirements.

## Slide 12
Lancashire and South Cumbria Neurodiversity Training Principles for Professionals
Consistency and Quality Assurance
Standardised Frameworks: Align with national standards (e.g., Oliver McGowan Mandatory Training)
Verified and Accredited Providers: Trainers with relevant qualifications and ethical standards
Evidence-based Content: Grounded in current research and best practices
Consistent messaging to families
Tiered Training Approach
Universal Training: For all staff across the system, at all levels, to raise awareness and reduce stigma
Targeted Training: For staff working directly with neurodivergent individuals
Specialist Training: For professionals requiring in-depth expertise
Inclusive and Person-Centred Design
Strengths-based Approach: Highlight unique strengths of neurodivergent individuals
Flexible Learning Formats: Visual, auditory, kinaesthetic; online and in-person options
Environmental Adjustments: Sensory-friendly training environments
Accessibility and Engagement
Clear Communication: Plain language, structured layouts, accessible fonts
Interactive Methods: Gamification, group discussions, assistive technologies
Pre- and Post-Training Support: Advance materials and follow-up resources
Ethical and Professional Conduct
Respect and Confidentiality: Uphold ethical standards and individual preferences
Continuous Improvement: Ongoing professional development and strategy evolution

## Slide 13: ND Tiered Training Offer for the System
Mapped training already on offer across the health, education and social care system – from awareness raising to clinical assessor training.
Developed minimum training requirements at each tier for autism, ADHD and FASD – aligning to national frameworks such as autism core competencies.
Working up training offer at each tier, with an initial focus on support for schools.

## Slide 14
Universal/Early Support
Targeted Support
Specialist Support
Step Up/Step Down Support
Shared Principles:
Support is based on need, not diagnosis
No child or family is turned away or closed to services because they are unable to engage
Support is joined up and continuous
Children, young people and families are at the centre
The whole family is considered, not just the child or young person
Lancashire & South Cumbria Needs Led Support: Principles & Tiers
General offers for families and children: classes, groups, courses, online resources.
Knowledge, skills, and consistent understanding for all professionals (education, health, social care, housing, voluntary sector).
Information, advice, and signposting for families.
Completion of Strengths and Needs Profile.
Peer support, practical tools, and coordinated early help from more than one service.
Team Around the Family (TAF) approach.
Courses, resources, and support groups that families can access with referral.
Early Help Assessment (EHA) as the entry point to some support.
Specialist interventions—reserved for those whose needs have not been met by earlier support.
Multi-professional, specialist support for more complex needs.
Joint planning meetings and ongoing involvement from services.
Consent and Child Voice
Crisis/Intensive Support
Multi-agency, mandatory response, Statutory assessments and interventions where needed, No need to access other tiers first

## Slide 15: ND Support Hub Model
Act as a fully integrated ‘all age’ strategic and operational hub for their area.
Coordinate and collaborate with local authority offers, local ND-specialists and community partners.
Map local ND related services and provision and maintain a live directory of local and regional ND support.
Use data and insights to drive service development and system learning.
Identify gaps in local support and co-design solutions with system partners.
Manage referrals and ensure seamless support pathways to provide information, advice and guidance (IAG) to families and individuals.
Support and deliver a programme of workshops, peer sessions and community engagement.

## Slide 16: Support hubs update
Funding for additional support secured for three years from ICB and range of ‘Lot A’ providers identified through collaboration with Spring North to run hubs in each area:
‘Lot B’ providers identified to be commissioned for specialist support to meet gaps.
National Lottery - Solidarity Fund £1.2 million over 5 years
Spring North submitted bid for match funding in September – outcome expected by April 2026.
Spring North to support provider development – links with training workstream.
Work as a partnership to define the hub model.
Area | C&YP | Adults
North Lancashire & South Cumbria | Triple A | Triple A
Central Lancashire | Key | Key
Blackpool, Fylde & Wyre | Communicate SLT | Communicate SLT
West Lancashire | Lancashire Mind | Lancashire Mind
East Lancashire and BwD | CANW (Existing Commission) | Blackburn Rovers

## Slide 17: Proposal Sensory Processing Pilot - Targeted Offer
Parent training (face to face and online)
Sensory Lead training for schools and settings
Training for LA SEND Teams including EPs, SATs, Early Years Advisors, SENDIASS, Virtual schools
Training for health professionals
Training for social care professionals
Resources
Drop ins for advice including for those educated at home

## Slide 18: Communications and Engagement
Communications strategy agreed.
Stakeholder mapping undertaken.
ICB webpage established to hold updates.
Regular briefings for all stakeholders to be shared via ICB website.
Workshops to be arranged to review and sense check communications and vision.

## Slide 19: Task Groups
  Profiling Tool
  Based on Portsmouth Model
  Building on work undertaken in the North East and North Cumbria ICB
  Fully digitalised and integrated into app
  Developing an ND profile for each child
  Pathological Demand Avoidance (PDA)
  Development of a system wide Position Statement through co-production
  Training and education in understanding of presenting need and support strategies
  Consistency in how all agencies engage and work where PDA is being raised

## Slide 20: Autism Pathway in Central and West Lancashire
Current postion:
LSCFT closed the referral pathway for ASD for school aged children in Central and West Lancashire in Spring 2025.
BTH have been providing a triage function for referrals as an interim measure.
Children and young people accepted are placed on a waiting list.
ICB is considering options for future commissioning of a full assessment pathway in Central and West Lancashire.

## Slide 21: How to get involved
If you are interested in being part of any of the workstreams please contact: lscicb.cypsend@nhs.net
We are particularly looking for involvement in the following workstreams:
  Training & Education
  Needs Led Support
  Digital
  PDA
  Sensory
  Comms & Engagement
Parent carer forums are engaged in all workstreams and wider engagement with families will take place going forward.

## Slide 22
Web lancashireandsouthcumbria.icb.nhs.uk | Facebook @LSCICB | Twitter @LSCICB