## Sheet1
Finding Theme and SRO | Recommendation |  | Action Owner | Ease of Implem-entation | Timescale | Management Response (within identified timescale) | Lead | Date due by | Status* On track Delayed Completed | Date for Delivery | Key actions | Progress update 30.10.25 | Progress update 31.12.25 | Progress update 10.04.26
Strategy | 1.1 |  | Sam Proffitt | Easy | 1 - 4 Weeks | Launch refreshed business case format and guidance. | Alex Wells | 21.08.25 | Completed | 30.07.25 | Develop revised business case template and guidance | Template has now been developed and process aligned to CRG processes. | Completed | Completed
[10 empty] | 21.08.25 | Commence re-launch of template and refreshed guidance | Commenced, template is being issued. Series of engagements and communications activities planned (BSG, staff newsletter, intranet) | Template now in use for all CRG requests - any January submissions will use new template. BSG update tabled for January. Drop-in engagement sessions planned early Feb | Completed
SRO: Sam Proffitt | [5 empty] | Provide training and support for staff (ongoing) | Alex Wells | 21.08.25 | Completed | 30.08.25 | Publish template and guidance on intranet | To be published on intranet w/c 03.11.25 | Guidance issued out - proposed that any forthcoming business case submissions into CRG now use revised template for January meetings and onwards | Completed
[10 empty] | 30.08.25 | Develop online video to provide overview of guidance | To be scheduled for completion by end November | Online guidance to be developed in conjunction with planned drop-in sessions to walk through process with users. This to be condcuted during February (unable to schedule sooner due to other comms commitments for these sessions). | Completed - forms part of changes in decision making processes as part of organisational restructure.
[10 empty] | 30.09.25 | Presentation at key engagement meetings e.g. CRG | To be scheduled for CRG and BSG in November | Drop in sessions planned for February as referenced above | Completed - forms part of changes in decision making processes as part of organisational restructure.
| 1.2 | Address health inequalities in future service changes, through both the strategic planning round and business cases. | Craig Harris | Moderate | 4 - 12 Weeks | Explicitly include inequalities impact assessment in commissioning intentions process and refreshed business case format | Alex Wells | 16.10.25 | Completed | 31.01.26 | As above and in line with revised NHSE guidance on impact assessments | Paper to be presented to Quality Committee w/c 03.11.25 which reflects revised NHS guidance. This offers a simplified screening process and also incorporates EHIIRA. | Process agreed for incorporation of EHIIRA into current Impact Assessment template. Standardised process updated with new guidance published on Intranet. Rollout of new processes started with revised QIA completed in November. Other domains (Equality & Diversity, Sustainability, Value Based Healthcare) to be rolled out from January. Drop in sessions to walk through revised processes in place 29th Jan | Completed
Mark Bakewell
Commissioning and Contracting | 2.1 | Develop a more sophisticated commissioning approach to address health inequalities, including variable payment mechanisms dependent on population need. | Craig Harris | Difficult | 12 - 26 Weeks | Review forthcoming national payment mechanism changes and consider development of aligned local approaches including integrated incentives to encourage and support neighbourhood care | Jess Williams Jane Cass Mark Bakewell | 27.01.26 | Completed | 23.07.25 | Commissioning SLT initial discussion | Will be completed as part of the development of the NHS Planning 5yr Commissioning Strategy. Mark Bakewell and Craig Harris both expressed support for developing an approach to increase funding to address health inequality although subject to affordability/next financial allocations. | Mark Bakewell picking up within DoF led contract discussions for short term 26/27. Trust Board debating investment strategy and market management strategy imminently and this should feature in development of 5ySCP. | NHSE developing Neighbourhood Payment guidance which the ICB is contributing to.
|  |  | Mark Bakewell | [6 empty] | 15.09.25 | Proposed workshop with planning, commissioning, contract management, population health and finance colleagues | As above. | Workshops for quantifying are on-going. To address financial challenge, there will be significant programmes in Neighbourhoods (also incorporating Frailty and UEC) and in OPD. Task and Finish “sprint” programme has been set up and initial meetings to ascertain ambition is tomorrow (9th Dec). 3 Neighbourhood workshops are scheduled in January with the second one bringing together those working in Place with Frailty, UEC on a specific footprint to define the activity shift targets
SRO: Craig Harris | [9 empty] | 30.09.25 | Review of national payment mechanism changes | As above | Mark Bakewell to advise on national timeframes
[10 empty] | 15.10.25 | Understand the potential for VCFSE to support delivery | As above | To be picked up in the assessment of market opportunities within 5YrSCF
| 2.2 | Conduct a detailed review of the capacity and capability of commissioning and finance teams to actively performance manage the LES (and other) contracts. | Sam Proffitt Craig Harris | Difficult | 12 - 26 Weeks | Consider capacity and capability as part of current organisational design process | Craig Harris | 27.01.26 | Completed | 15.09.25 | Discussions between commissioning, clinical finance and contracting teams about transitional operating arrangements to ensure integrated working | Organisational redesign has been paused untl the next financial year. This will be picked up as part of that work | This will be picked up as part of the operating model and structure work that is currently being progressed. | Formed part of process to develop ICB operating model and structure and associated implementation process.
[10 empty] | 30.09.25 | Agree expectations and business arrangements | As above | As above
[10 empty] | Sep-Oct 25 | Staff consultation is expected to begin | As above | As above
[10 empty] | Oct-Dec 25 | Implementation of new structures | As above | As above
| 2.3 | Ensure joined-up commissioning between primary and secondary care with appropriate engagement for pathway redesign. | Craig Harris | Moderate | 1 - 4 Weeks | Implemented integrated contract and commissioning assurance meetings | Peter Tinson, Jayne Mellor, Fleur Carney | 21.08.25 | Completed |  |  | Completed | Completed | Completed
[6 empty] | Implemented new commissioning intentions process | Jess Williams | 21.08.25 | Completed |  |  | CI 2026-27 process is progressing as to agreed timescales. Aiming to recalibrate alongside NHS Planning. | Completed | Completed
[6 empty] | Informed new organisational design (integrated footprint commissioning teams) | Craig Harris | 21.08.25 | Completed |  |  | Completed | Completed | Completed
| 2.4 | Consider aligning finance and contracting under a single function. | Sam Proffitt | Difficult | 12 - 26 Weeks | Consider as part of current organisational design process | Craig Harris | 27.01.26 | Completed | 24.07.25 | Agreed as part of overall ICB organisational design | Organisational redesign has been paused untl the next financial year. This will be picked up as part of that work | This will be picked up as part of the operating model and structure work that is currently being progressed. | Formed part of process to develop ICB operating model and structure and associated implementation process.
[10 empty] | 15.09.25 | Discussions between commissioning, clinical finance and contracting teams about transitional operating arrangements to ensure integrated working | As above | As above
[10 empty] | 30.09.25 | Agree expectations and business arrangements | As above | As above
Industrial Action | 3.1 | Improve understanding of industrial action impacts. | Andy Knox | Moderate | 12 - 26 Weeks | Currently no industrial action underway | Wendy Lewis | 27.01.26 | Completed | 23.07.25 | Ongoing. Escalation processes identified and in place, should it need to be actioned | Completed | Completed | Completed
[6 empty] | Impacts and mitigations considered as part of EPRR process | Wendy Lewis | 27.01.26 | Completed | 23.07.25 | Ongoing. Escalation processes identified and in place, should it need to be actioned | Completed | Completed | Completed
SRO: Andy Knox | 3.2 | Enhance transparency and safeguard against conflicts of interest. | Andy Knox | Moderate | 12 - 26 Weeks | Review current generic staff training and explore inclusion of specific (case study based) training for clinical and managerial commissioning staff | Claire Moore | 27.01.26 | Completed | 29.07.25 | 29.07.25 and ongoing: Three training modules in place provided by NHSE. All staff mandated to complete module 1. Decision makers are mandated to complete level 2. Level 3 is for ICB chair and deputy only Transparency and safeguarding against conflicts of interest is supported through all staff providing their declaration of interests and ensuring these are managed in accordance with the policy. There is also quarterly reporting to the audit committee | Completed | Completed | Completed
[10 empty] | 30.09.25 | 30.09.25: Review compliance amongst clinical and managerial commissioning staff and report to commissioning SLT Review level 2 content and determine whether target group should be widened | 29.10.25 Review of training compliance for clinical leads conducted; compliance figures provided to P Tinson. Process for monitoring mandatory training compliance for clinicians to be reviewed with A Anderson. 08.10.25: Generic COI training is mandated for all staff and is evidenced through completion of the Level 1 Training Module. Current compliance rates are reported at 77%. From August 2025 the NHS England Level 2 role-specific training module: “Guidance on Managing Conflicts of Interests throughout the commissioning cycle” was enabled via ESR. Compliance rates for those staff in scope (i.e. those defined as decision makers as defined within the ICB’s Managing Conflicts of Interest Policy) is currently reported at 35%. End of Q3: Compliance against COI training will continue to be monitored through workforce reports to assess overall compliance against the Managing Conflicts of Interest role-specific training modules. Line managers are responsible for ensuring all staff (clinical and managerial) have completed relevant mandatory training; confirmation that mandatory training has been completed is discussed as part of the ICB’s appraisal process. Workforce data will be reviewed to ensure all relevant staff (clinical and managerial) are captured through current workforce reporting arrangements and have access to the training modules. Where staff are identified as “in scope” but do not have access to ESR they will be directed to the NHS Learning Hub and required to provide evidence of completion. | 17.12.25: A review of compliance has been undertaken against ICB mandated training modules for the Management of Conflicts of Interests (Level 1 and 2). The review has included clinical colleagues who work for or on behalf of the ICB who fall in scope of the ICB's policy and procedures for COI. To support colleagues, a communication from the ICB's Medical Director will be issued which provides details of how to access the training modules provided by NHS England for ICBs (both via ESR and the NHS Learning Hub) as well as a link to the ICB's declaration of interest form. The due date for completion of the training modules will be suggested as 27.1.26. The corporate team will monitor oversight of the declaration of interests received; uptake of COI training will be overseen through the HR/WIS reporting arrangements. | 13.02.26: Letter issued to CCPLs on behalf of ICB's Medical Director providing details of how to access the training modules and that evidence of training to be submitted to ICB. Letter also provided link to ICB's declaration of interests form. This action is now completed and compliance will be monitored as part of BAU.
| 3.3 | A clear stakeholder map needs to be developed with an agreed communications plan including key responsibilities ahead of any collaborative working or contract negotiations. | Craig Harris | Easy | 4 - 12 Weeks then on-going | Commissioning leads to review roles and responsibilities of current negotiation forums and propose any changes. | Peter Tinson Wendy Lewis Fleur Carney Jayne Mellor | 16.10.25 | Completed | 30.08.25 | Discuss in Commissioning SLT | Being discussed at Commissioning SLT on 19.11.25 | Completed for Primary Care. Clear process in place for Community and Secondary Care commissioning intentions and associated negotiations. | Completed
[10 empty] | 30.09.25 | SLT members to undertake review and report back to SLT | As above | As above | Completed
[6 empty] | PIDs for any significant collaborative service redesign to include stakeholder map and communications plan | Alex Wells | 16.10.25 | Completed | 23.07.25 | Stakeholder map and communications plan included in existing PID format | Completed | Completed | Completed
[10 empty] | 16.10.25 | Engage and socialise templates with commissioning teams | Completed | Completed | Completed
Business Case Process | 4.1 | Undertake a detailed review of the new business case process and associated templates. | Mark Bakewell | Easy | 1 - 4 Weeks | Launch refreshed business case format and guidance. Provide training and support for staff | Alex Wells | 21.08.25 | Completed |  | See 1.1 above | See 1.1 above | See 1.1 above | See 1.1 above
SRO: Stephen Downs | 4.2 | Establish clear financial parameters for commissioning changes, with clarity on what requires a business case and the associated governance. | Mark Bakewell | Easy | 4 - 12 Weeks | Produce a simple schematic outlining commissioning decision making arrangements and documentation required | Alex Wells | 16.10.25 | Completed | 30.09.25 | Schematic to be developed incorporating 4.3 (governance forums for decision making), 5.2 (requirement for governance approval prior to binding communication to stakeholders) and 5.3 (limit CEO communication to final decisions, or the resolution of essential escalations) | This forms part of 4.1 | This forms part of 4.1 | This forms part of 4.1
| 4.3 | Clarify governance forums responsible for decision-making on business cases, including where Board and NED approval is required. | Mark Bakewell | Easy | 4 - 12 Weeks | See 4.2 | Charmaine McElroy / Andy K / Craig Harris | 16.10.25 | Completed |  | See 4.2 | Emerging proposal is with Craig and Andy K for discussion with Debra Atkinson and Aaron to shape further before seeking formal executive approval, | No further update | This action forms part of the review currently being undertaken by Debra Atkinson and Alex Wells on the Target Operating Model so has now been superseded.
| 4.4 | Ensure all financial numbers are validated and properly included in the business case for decision making. | Mark Bakewell | Easy | 1 - 4 Weeks | Refreshed business case format and guidance to reinforce requirement for finance engagement and sign off | Alex Wells | 21.08.25 | Completed | 23.07.25 | Gateway stages for finance engagement and sign off included within business case format and guidance | Completed | Completed | Completed
Leadership | 5.1 | Define the responsible Executive from the outset. | Craig Harris | Easy | 1 - 4 Weeks | Commissioning executive responsible for all commissioning proposals | Craig Harris | 21.08.25 | Completed |  |  | Completed | Completed | Completed
SRO: Sam Profitt |  |  | Sam Proffitt
| 5.2 | Avoid binding correspondence with stakeholders before governance approval. | Craig Harris | Moderate | 1 - 4 Weeks | See 4.2 | Charmaine McElroy / Andy K / Craig Harris | 21.08.25 | Completed |  | See 4.2 | Emerging proposal is with Craig and Andy K for discussion with Debra Atkinson and Aaron to shape further before seeking formal executive approval, | No further update | This action forms part of the review currently being undertaken by Debra Atkinson and Alex Wells on the Target Operating Model so has now been superseded.
| 5.3 | Limit CEO communication to final decisions, or the resolution of essential escalations. | Craig Harris | Easy | 1 - 4 Weeks | See 4.2 | Charmaine McElroy / Andy K / Craig Harris | 21.08.25 | Completed |  | See 4.2 | Emerging proposal is with Craig and Andy K for discussion with Debra Atkinson and Aaron to shape further before seeking formal executive approval, | No further update | This action forms part of the review currently being undertaken by Debra Atkinson and Alex Wells on the Target Operating Model so has now been superseded.
Communication and Stakeholder Management | 6.1 | Improve formal and informal communication to facilitate negotiation, see recommendation 3.3. | Craig Harris | Difficult | 12 - 26 Weeks | See 3.3. In response to new organisational design review informal and formal communication touch points | Peter Tinson Wendy Lewis Fleur Carney Jayne Mellor | 27.01.26 | Completed |  | See 3.3 Subject to agreement of organisational design | Organisational redesign has been paused untl the next financial year. This will be picked up as part of that work | To be picked up as part of operating model engagement and feedback | Formed part of process to develop ICB operating model and structure and associated implementation process.
SRO: Craig Harris | 6.2 | Balance collaborative approaches with effective negotiation. | Craig Harris | Difficult | 12 - 26 Weeks | See 3.3 | Peter Tinson Wendy Lewis Fleur Carney Jayne Mellor | 27.01.26 | Completed |  | See 3.3 | Organisational redesign has been paused untl the next financial year. This will be picked up as part of that work | To be picked up as part of operating model engagement and feedback | Formed part of process to develop ICB operating model and structure and associated implementation process.