## Slide 1
Summary Review of Draft Primary Care Action Plans
NHS Lancashire & South Cumbria ICB
May 2026
Notes: Standard title slide

## Slide 2: Primary Care Action Plans
As part of the Medium-Term Planning process, ICBs are required to complete a Primary Care Action Plan for 2026/27, ensuring plans cover a three-to-five-year period, with a detailed Year 1 plan for 2026/27.
Plans should focus on practical, deliverable actions, build on the feedback provided on Strategic Commissioning Plans (SCPs), and draw on evidence-based approaches and proven best practice to improve access and outcomes.
ICBs should complete and submit PCAPs to Regional teams by 12noon 28th May 2026.
In addition to the above, the North West Primary Care team have built in touch points with ICBs to support and oversee ICB development of plans including a review of draft plans submitted on 1st May.
The following slides provide the headline summary review of the ICBs draft plan, this supplements details provided via email, sent Wednesday 6th May and discussions undertaken at the touch point session of the 6th May 2026 also
The North West Primary Care team remains available for individual system meetings as required
Systems are strongly encouraged to share their plans with one another to share learning and best practice
Requirement, Timelines and Approach

## Slide 3: Primary Care Action Plans
A respectable first draft plan that built on from the ICBs Integrated Strategic Commissioning Plan.
The plan confirms a trajectory for delivery of the General Practice Same Day Urgent appointments.
The identification and management of challenged GP providers in terms of variation is referenced in the plan.
The plan addresses improvements to be made to GP Access and Dental Access.
The plan also addresses the commissioning of sight checks in special educational settings,
The ICB have provided verbal assurance at touch point session that governance, oversight and assurance of plans for sign off are in situ as are arrangements for tracking of delivery, with this to be made explicit in final written plan submission.
It is recognised the document is an iterative Plan which will be revisited throughout the year and delivery will be tracked against plan from baseline.
There is an acknowledgment that further supporting narrative may be in other ICB materials; any such relevant detail should be included in the primary care action plan and cross-references is to be made clearer in final submissions by 28/05.
Strengths of Draft Plan

## Slide 4: Primary Care Action Plans
General Principles
Final submission should set out clearer SMART actions, timelines and ownership.
Mitigations to highlighted risks in all areas should be included
Include the local methodology for identifying and managing challenged providers across all Primary Care groups and the support being provided.
Provide stronger detail on all challenged providers, including numbers, milestones, support actions and intervention timescales.
Show how continuous improvement and learning from June 2025 Primary Care plans are being applied.
Clarify internal ICB governance arrangements for oversight and monitoring.
Confirm stakeholder engagement in plan development and delivery.
Set out more detailed actions to address contractual non-compliance at practice level and recording of actions.
Areas to Strengthen in Final Submission

## Slide 5: Primary Care Action Plans
General Practice
Re Urgent same day - NHSE will seek to collab with the ICB on those most challenged providers when they are identified during M1-4. Specific provider visibility for any struggling with this will be needed as ministerial attention to this delivery metric expected to be high.
Re Resiliency, winter planning and surge capacity: acknowledging some listed measures and interventions may operate/flex year-round, there is an absence of specificity with regards outcomes/dates/milestones
Front Door Access/Opel - When will actions be implemented, what is the resource and offer to practices when escalation occurs
Clinical Capacity - more detail required about support offer from training hubs and timescales for actions to be completed such as PCN ARRS roles being maximised etc
The recent ministerial focus on GP/Patient ratios needs to include greater detail to meet specific asks in relation to this area of focus
Areas to Strengthen in Final Submission
Dental
The PCAP needs to include the relevant detail / sections from the dental commissioning plan rather than referencing separate documents and referring to cells as it is difficult to assess the appropriateness of the plan. This is to ensure the plans describes the actions, the data, the timelines and the resource to deliver the plan.
Procurement of Dental SES - The plan is not specific enough, it needs to set out the actions and timelines from procurement to implementation to provide assurance the service will be delivered in year.
Pharmacy
Greater emphasis on Community Pharmacy and maximisation of Pharmacy First to support access. The pharmacy plan needs to include the relevant detail / sections from the pharmacy access scheme rather than referencing separate documents as it is difficult to assess the appropriateness of the plan. This should include detail as to the actions, the data, the timelines and the resource to support and challenge provider non contractual compliance and or unwarranted variation.
Introduce prescribing based services - How will monitoring of prescribing be aligned with existing Meds Optimisation governance, performance and improvement and what are the mitigations to the highlighted risks
Embedding pharmacy clinical services - What data can ICB use in the absence of national data? More detail required about maximising NHS 111 data and referrals and calls ended etc